## Read Me First
Azure Chat Bot Project — AWS Rebuild Tracker
Project re-scoped to AWS. Updated column set + milestone guide below.
1. What changed
Platform pivot | Customer has moved this from Azure to AWS. The project restarts from access provisioning — the milestone list below reflects an AWS build, not the original Azure one.
New columns added | Phase, Priority, Status, and % Complete have been added to the original 9. This gives the dashboard enough structure to group by phase and show real progress bars, and makes the sheet easy for a Python script to parse later.
2. The 12 columns, explained
SN | Row order. Keep the sheet sorted by Target Date and this stays meaningful.
Milestone | Name the outcome, not the activity — "AWS account access provisioned" rather than "Setting up AWS access".
Phase | Which stage of delivery this belongs to. Pick from the dropdown (Access & Governance / Infra Build / Bot Platform / Dev / Testing / Security / UAT / Deployment / Handover). This is what lets the dashboard show phase-wise progress.
Task Owner | Person on your team accountable for this milestone. One name per row.
Customer Owner | Counterpart on the customer side who needs to act, approve, or provide input.
Priority | High / Medium / Low — use the dropdown. Helps you and management see what to focus on if something slips.
Start Date | Date work actually starts. Leave blank until it does.
Target Date | The date you're committing to. Fill this in up front for every milestone — the dashboard timeline is built from this.
Actual Date | Date it was actually completed. Leave blank until done.
Status | Use the dropdown: Not Started / In Progress / Completed / Blocked / Delayed. Keep this current — it's the main field the dashboard reads.
% Complete | A number 0–100. For milestones that are one clean deliverable, this will mostly jump from 0 to 100 — that's fine. Use partial numbers for longer-running items like development or testing.
Reason for Delay | Only fill in when Target Date has passed without an Actual Date, or the milestone finished late. One factual sentence is enough.
3. Weekly habit (5 minutes)
Before your status meeting | Update Status and % Complete for anything that moved, and fill in Actual Date for anything finished. That's all the dashboard needs.
If a date will slip | Only change Target Date if the milestone hasn't started and you're genuinely re-planning. If it's already overdue, leave Target Date as-is and add a Reason for Delay instead.
4. For the Python app (later)
Keep headers exactly as-is | Column headers are on row 1 of the Tracker tab. Don't rename or reorder them — your script (and the dashboard's import) will match columns by header name.
Use the dropdowns | Status, Phase, and Priority are restricted to fixed lists (data validation) so the values your script sees are always consistent — no "in progress" vs "In-Progress" mismatches.
5. Alternate-day sync rhythm
Tracker tab = milestone level | Only update Status / % Complete / Last Updated when something genuinely changed. Most milestones won't move every single sync — that's normal.
Sync Log tab = day-to-day | Use this for the actual conversation each sync — quick updates, blockers, next steps. Keeps the Tracker tab clean for management reporting.
Stale-row flag | Any milestone whose "Last Updated" is more than 6 days old (about 3 syncs) gets highlighted amber on the Tracker tab — a quick way to spot what's being overlooked.
6. Two-level tracking: Milestones vs Sub-Tasks
Tracker tab | Your 18 high-level milestones (1-2 weeks each). This is what management sees.
Sub-Tasks tab | Break each milestone into the day-to-day tasks your team is actually doing. Pick the parent Milestone from the dropdown in column A so it links back correctly.
% Complete is now automatic | The Tracker's % Complete column is now a formula — it counts how many Sub-Tasks under that milestone are marked "Completed" out of the total. Check off sub-tasks as you go, and the milestone-level % updates itself. Don't type into that column anymore — it will get overwritten by the formula.
Status stays manual | Keep setting Status on the Tracker tab yourself (Not Started / In Progress / Completed / Blocked / Delayed) — % Complete alone doesn't tell you if something is blocked.
7. New tabs added
Executive Summary | A one-page, Excel-native snapshot (KPIs + charts) auto-calculated from the Tracker. Handy if you need to share a quick status without opening the web dashboard.
Risk-Issue Log | Track things that could go wrong (Risks) or already have (Issues), separate from day-to-day delay reasons. Review this briefly at each sync.
Stakeholders | One place for who's who — your team and the customer's — and their RACI role. Fill this in early; it'll save you time later.
Change Log | A short history of major changes (like the Azure→AWS platform switch already logged as the first entry). Add an entry whenever scope or a committed date genuinely changes.
8. RAG Status & Remarks columns
RAG Status (auto) | Calculated for you — Green (on track / completed on time), Amber (completed late, or due within 7 days), Red (overdue, or marked Blocked). Shows "-" until a Target Date is set. Don't type into this column — it's a formula.
Remarks / Next Steps | A free-text field for anything worth noting on a milestone that's going fine — not just the ones that are late. Use "Reason for Delay" only for actual delays; use this for everything else, like what's planned next.
9. MOM Tracker
One row per action item | Meeting Date/Title/Attendees repeat across rows from the same meeting — this makes it easy to filter the whole sheet by Owner or Status across all meetings, not just read one meeting at a time.
After each meeting | Fill in Discussion Summary, Decisions, and Action Items with Owner + Due Date. Update Status as items close. Set "Shared with Mgmt" to Yes once you've sent that meeting's update.

## Executive Summary
Azure Chat Bot (AWS Rebuild) — Executive Summary
Auto-calculated from the Tracker tab. Refresh (F9) after updating milestone data.
Total Milestones | 18
Completed | 0
Overdue | 0
Due Soon (7 days) | 0
Overall % Complete | 25
Status Breakdown |  | Phase-wise Avg. % Complete
Status | Count | Phase | Avg %
Not Started | 18 | Access & Governance | 25
In Progress | 0 | Infra Build | 0
Completed | 0 | Bot Platform | 0
Blocked | 0 | Development | 0
Delayed | 0 | Testing | 0
|  | Security | 0
|  | UAT | 0
|  | Deployment | 0
|  | Handover | 0
Helper Data — auto-calculated, feeds the charts above. Don't edit.
RAG | Count | Priority | Count | Risk Impact (Open) | Count | Segment | Value
Green | 18 | High | 13 | High | 1 | Complete | 25
Amber | 0 | Medium | 5 | Medium | 1 | Remaining | 75
Red | 0 | Low | 0 | Low | 0
Phase | Count | Owner | Count
Access & Governance | 2 | Priya Sharma | 0
Infra Build | 3 | Arjun Mehta | 0
Bot Platform | 3
Development | 3
Testing | 2
Security | 1
UAT | 1
Deployment | 2
Handover | 1
|  | Unassigned | 18

## Tracker
SN | Milestone | Phase | Task Owner | Customer Owner | Priority | Start Date | Target Date | Actual Date | Status | % Complete | Reason for Delay | Last Updated | RAG Status | Remarks / Next Steps
1 | AWS Landing Zone / Account Access Provisioned | Access & Governance |  |  | High |  | 2026-07-15 |  | Not Started | 50 |  |  | Green
2 | IAM Roles, Policies & Access Controls Setup | Access & Governance |  |  | High |  | 2026-07-22 |  | Not Started | 0 |  |  | Green
3 | VPC & Networking Setup | Infra Build |  |  | High |  | 2026-08-05 |  | Not Started |  |  |  | Green
4 | Core AWS Services Provisioning (Compute, Storage, DB) | Infra Build |  |  | High |  | 2026-08-19 |  | Not Started |  |  |  | Green
5 | CI/CD Pipeline Setup | Infra Build |  |  | Medium |  | 2026-08-28 |  | Not Started |  |  |  | Green
6 | Bot Platform Setup (Amazon Lex / Bedrock Agent) | Bot Platform |  |  | High |  | 2026-09-11 |  | Not Started |  |  |  | Green
7 | Conversation Design (Intents & Flows) | Bot Platform |  |  | High |  | 2026-09-18 |  | Not Started |  |  |  | Green
8 | NLU Model Training & Tuning | Bot Platform |  |  | Medium |  | 2026-09-30 |  | Not Started |  |  |  | Green
9 | Knowledge Base Integration (Kendra / Bedrock KB) | Development |  |  | High |  | 2026-10-14 |  | Not Started |  |  |  | Green
10 | Backend/App Logic Development | Development |  |  | High |  | 2026-10-28 |  | Not Started |  |  |  | Green
11 | Channel Integration (Web / Teams / Slack) | Development |  |  | Medium |  | 2026-11-06 |  | Not Started |  |  |  | Green
12 | Internal QA & Functional Testing | Testing |  |  | High |  | 2026-11-18 |  | Not Started |  |  |  | Green
13 | Performance & Load Testing | Testing |  |  | Medium |  | 2026-11-25 |  | Not Started |  |  |  | Green
14 | Security & Compliance Review | Security |  |  | High |  | 2026-12-04 |  | Not Started |  |  |  | Green
15 | UAT with Customer | UAT |  |  | High |  | 2026-12-16 |  | Not Started |  |  |  | Green
16 | Production Environment Setup | Deployment |  |  | High |  | 2026-12-23 |  | Not Started |  |  |  | Green
17 | Go-Live / Production Deployment | Deployment |  |  | High |  | 2027-01-06 |  | Not Started |  |  |  | Green
18 | Hypercare, Documentation & Handover | Handover |  |  | Medium |  | 2027-01-20 |  | Not Started |  |  |  | Green
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
Formulas:
RAG Status = IF([Status]="Blocked","Red",IF([Actual Date]<>"",IF(OR([Target Date]="",[Actual Date]<=[Target Date]),"Green","Amber"),IF([Target Date]="","-",IF([Target Date]<TODAY(),"Red",IF([Target Date]<=TODAY()+7,"Amber","Green")))))

## Sync Log
Date | Milestone / Workstream | Update Owner | Key Update | Blockers / Issues | Next Steps | Next Sync Date
Tip: log the highlights from each alternate-day sync here. Update Status/% Complete on the Tracker tab only when something actually changed.

## Sub-Tasks
Milestone | Sub-Task | Owner | Start Date | Target Date | Status | Notes
AWS Landing Zone / Account Access Provisioned | Raise AWS account request with customer |  | 2026-07-10 | 2026-07-11 | Completed
AWS Landing Zone / Account Access Provisioned | Confirm billing & org structure |  | 2026-07-11 | 2026-07-12 | Completed
AWS Landing Zone / Account Access Provisioned | Set up root account MFA |  | 2026-07-12 | 2026-07-13 | In Progress
AWS Landing Zone / Account Access Provisioned | Validate access with team |  | 2026-07-13 | 2026-07-15 | Not Started
IAM Roles, Policies & Access Controls Setup | Define role structure (dev/test/prod) |  | 2026-07-16 | 2026-07-18 | Not Started
IAM Roles, Policies & Access Controls Setup | Create IAM policies |  | 2026-07-18 | 2026-07-20 | Not Started
IAM Roles, Policies & Access Controls Setup | Assign roles to team members |  | 2026-07-20 | 2026-07-22 | Not Started

## Risk-Issue Log
ID | Type | Description | Related Milestone | Impact | Likelihood | Mitigation / Action Plan | Owner | Status | Date Raised | Date Resolved
1 | Risk | AWS access/IAM approvals may take longer than planned due to customer's internal governance process | AWS Landing Zone / Account Access Provisioned | High | Medium | Escalate access requests early; get a named approver on customer side |  | Open | 2026-07-01
2 | Risk | Bedrock/Lex service limits or region availability may differ from what was used on Azure | Bot Platform Setup (Amazon Lex / Bedrock Agent) | Medium | Medium | Confirm service quotas and region support before design starts |  | Open | 2026-07-01

## Stakeholders
Name | Role / Title | Organization | RACI | Email | Notes
Priya Sharma | Delivery Lead | Ours | Responsible
Arjun Mehta | Cloud/Infra Engineer | Ours | Responsible
| Project Sponsor | Customer | Accountable
| Customer IT/Security Contact | Customer | Consulted

## Change Log
Date | Milestone | Field Changed | Old Value | New Value | Reason | Changed By
2026-07-01 | All milestones | Scope/Platform | Azure-based build | AWS-based build | Customer requested platform change from Azure to AWS

## MOM Tracker
Azure Chat Bot (AWS Rebuild) — Minutes of Meeting (MOM) Tracker
One row per action item. Meeting details repeat across rows for the same meeting — this keeps it easy to filter/report by owner or status.
Meeting Date | Meeting Title | Attendees | Discussion Summary / Key Points | Decision Made | Action Item | Action Owner | Due Date | Status | Shared with Mgmt
2026-07-02 | Team Kickoff — Introductions & Milestone Review |  | Reviewed AWS rebuild milestones with the team; discussed Azure→AWS pivot context. |  | Assign Task Owner to every milestone on the Tracker tab |  |  | Open | No
2026-07-02 | Team Kickoff — Introductions & Milestone Review |  |  |  | Confirm alternate-day sync time with the team |  |  | Open | No
| Technical Discussion — Solution Architect | [6 empty] | Not Started | No